## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | Connect Four Game
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2022-07-09 | Mason | Board does not need to hold circle or rectangle objects to render spaces and columns. It can render the board based on the board structure alone everytime there is a change. | Closing | Design | Low | Mason | 2022-07-09 | 2 hours | Completed |  | 2022-07-09 | 1 hour | Lack of understanding of how pygame graphics work; did not know there was a feature that simply draws on the screen without the need to store information in memory
2 | 2022-07-09 | Mason | The board interface and remote player need access to same element, (connection to server) Its redundant for them to both have the object. | Closing | Design | Low | Mason | 2022-07-10 | 2 hours | Completed |  | 2022-07-10 | 1.5 hours | Adhered to inheritance for determining input type without considering the alternative of assigning numbers to correspond to input types. | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 2022-07-09 | Mason | Sometimes, board fails to render opponent's last played move in multiplayer game. Nevertheless the board data structure changes to reflect the move consistently. | Planning | Development | High | Mason | ? | 6 hours | Completed |  | 2022-07-21 | ? | The fix appears to have dissappeared while I was refctoring the code. There is no known explanation for why it occured. | Completed | Low | Planning | Requirements
4 | 2022-07-12 | Mason | In a multiplayer game, pieces are sometimes inexplicably placed against intentions of players | Closing | Testing | High | Mason | 2022-07-12 | 6 hours | Completed |  | 2022-07-14 | 8 hours | The event queue was not cleared before the next player was asked for their move. ie. if the player double clicked a column, their move would register first and then when it was there turn again the second clicks event would fill in the next move automatically. |  |  | Executing/Controlling | Design
5 | 2022-07-12 | Mason | Game crashes occasionally after a move is played. | Executing/Controlling | Testing | High | Mason | 2022-07-12 | 6 hours | Completed |  | 2022-07-16 | 1.75 hours | The system attempted to place a value out of bonds of the array that tracks the board layout. This occured only when a piece was placed in a full column. This could have been solved sooner if more attention was payed to the terminal log that was alerting this very premise. | New
6 | 2022-07-21 | Mason | Revisiting previous moves the second time using the rewind function appears to erase the moves that are observed more than once | Executing/Controlling |  | High | Mason | 2022-07-21 | 3 hours | Completed |  | 2022-07-22 | 2 hours | Because numpy references its arrays using pointers passing a numpy value to a different alias does not make a copy of the values that youa re working with. Decoding the data stored in these numpy arrays required me to integer divide the encoded values in a for loop until they were zero. Since I used a numpy array to reference these encoded board representations, this integer division would affect the values stored in memory. To fix I simply made a temporary variable to hold the encoded values. |  |  |  | Documentation and Training
7 | 2022-07-14 | Mason | Parts of the board are missing upon lanching the game. They only reappear when the player using the window with missing components makes their first move. | Executing/Controlling | Testing | High | Mason | 2022-07-14 | 8 hours | Completed |  | 2022-07-18 | 1.75 hours | The system attempted to place a value out of bonds of the array that tracks the board layout. This occured only when a piece was placed in a full column. This could have been solved sooner if more attention was payed to the terminal log that was alerting this very premise. |  |  |  | Deployment
8 | [17 empty] | Post-Deployment
9
10
11
12
13
14
15
16
Note on E10: Choose from the drop down box.
Note on F10: Choose from the drop down box.
Note on G10: Choose from the drop down list
Note on K10: Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).